## Metadata
S. No. | Data Elements | Values
1 | Title | Grenada Enterprise Architecture Roadmap Toolkit
2 | Title Alternative | GEA –RT
3 | Document Identifier | GEA.RT.001
4 | Document Version, Month, Year of Release | Version 0.1, December 2024
5 | Present Status | Draft
6 | Publisher | Department of ICT, Government of Grenada
7 | Date of Publishing | To be updated
8 | Type of Standard Document | Toolkit
9 | Enforcement Category | Mandatory
10 | Creator | DTA, Government of Grenada
11 | Contributor | Names of participating MDAs and industry body
12 | Brief Description | This document provides an otoolkit to be leveraged by MDAs (EA focal points) to develop the MDA or Government organisation level roadmap.
13 | Target Audience | MDA, EA Focal Points, Consultants
14 | Owner of Approved Standard | Office of Prime Minister
15 | Subject | Enterprise Architecture
16 | Subject Category | Institutional Mechanism
17 | Coverage: Spatial | Grenada
18 | Format | PDF (PDF/A at the time of release of the final standard)
19 | Language | English
20 | Copyrights | Government of Grenada

## About
About the toolkit
Nos. | Remarks
1 | The toolkit is intended to support in a roadmap activity. This is divided into specific tabs which are used to manage specific activities in the course of the brainstorming and ideation session.
2 | The typical flow proposed for the roadmap session includes - a) Ideation - encouraging participants to provide suggestions for candidate initiatives which could be a part of the digital transformation exercise. b) Alignment - we use this session to assess the fitment of the candidate initiatives with our vision and priorities c) Classification - attempt to map the candidate initiatives into potential work areas d) Prioritization - we acknowledge the contraints (benefits, risks, timelines, budget) to prioritize the candidate initiatives e) Roadmap - we prepare a target state roadmap with the potential initiatives on a fixed timeline
3 | The above activities allows us to quickly establish the potential initiatives and focus on the top priority initiatives.
4 | However, post the roadmap it is essential to document and detail out the work packages for each of the initiative that have been selected to be a part of the digital transformation initiative.
5 | A work package is expected to include: a) Overview - description of work package, stakeholders, budget, timelines b) Business case - alignment to National Vision and Priority areas, objectives, benefits, Services (if applicable), dependency, policy c) Implementation - Phases, Procurement needs, Resourcing needs, Design, Change and Capacity requirement, Assumptions

## Guide
Toolkit usage guidelines
Activity 1 - Initiatives identification and Activity 2 - Initiatives consolidation
1) Discuss services (front-end) delivered to your users (citizens / taxpayers / business / tourists / other groups) by your entity. 2) Identify existing challenges and potential improvement opportunities you can see 3) Ideate the potential initiatives which can help with teh challenges and opportunities for improvement. 4) Initiaitves should be classified under one group (1 - Enabling initiative OR 2 - Common / Reusable OR 3 - MDA / Sector specific) 5) There should be a responsible entity who owns this initiative 6) The initiative could be around the following areas - enabling rules and regulations, capacity development and training to cater to a specific digitization initiative, digitization of a manual service, improvement in an existing service, transformation of service delivery process, procurement of infrastructure, digital upskilling, skilled resources). 7) Please try to ideate and mention a specific initiative instead of a generic initiative
Initiative Name | Short name for the initiative
Group | Identify the group this initiative falls under: 1- MDA / Entity specific service 2 - Common / Shared / Reusable service 3 - Enhancement initiative
Entity | Identify the entity who will be responsible for implementing this initiative
Dependency | Identify the dependencies of this initiative on other initiative
Remarks | Further description to expand and describe the initiative
Activity 3 – Initiatives aligned to digital vision
1) This exercise intends to map the initiatives identified to the strategic digital vision and themes identified 2) As a rule, a initiative should be either an enabling / pre-requisite category or should be aligned to at least one strategic theme which has been agreed upon.
Improve service delivery | Map the initiative to the strategic themes which have been identified in Day 1 of the workshop. It is important to note that specific initiatives will qualify as proposed candidate initiatives if they are aligned to one or more of the strategic themes of the digital vision.
Encourage Business / Investments
Improve Quality of Life
Improve Operational efficiency
Sustainability & Resilience
Activity 5 – Initiatives classification
1) This exercise is to map the initiatives into further categories which allows us to view a detailed breakdown and understand the initiative. 2) Various dependencies, requirements should be assessed by the audience for preparing this view.
Quick-win | An initiative which can be executed within 6 months qualifies as a quick-win
Reusability / Shared service | If the initiative falls under common / reusable initiative group or caters to the requirement of more than one government entity
Sourcing | This will be marked if the initiative requires procurement or external sources to implement
Standardization or compliance | This will be marked if the initiative caters to standardization or compliance requirement required as per domain or business requirements or contractual specifications
Service | This will be marked if the initiative intends to provide a government service to citizen / business / others
Policy | This will be marked if the initiative requires the review or development of a policy / regulation
Activity 6 - Initiatives prioritization
1) This exercise enables us to breakdown and assess the initiative from the benefit, execution, cost, risk and time perspective. 2) Each initiative will be qualitatively assessed under each of these parameters to arrive at a consolidated scoring mechanism 3) This is an indicative dashboard to enable us to prioritise the initatives. However, we can overrule the mechanism for specific initiatives which we believe is required irrespective of the cost / time / risk quotients.
Business benefits
Governance | High - focus on analytics, reporting solutions which enables monitoring or rules / policies which is enable the governance Medium - the initiative allows us to manage and have oversight of government services and operations but additional efforts will be required to ensure end-to-end governance Low - there is no governance component or limited requirements for governance
Service delivery | High - The initiative directly focus on a government service delivery and will benefit users to a high extent Medium - the initiative indirectly will help the government to improve the service delivery but does not directly support or enable any services Low - There is limited or no benefit linked to this initiative for the service delivery
Ease of operations | High - The initiative will help improve the overall government operations to a large extent Medium - The initiative directly does not impact operations but implementation will help reduce overall time and cost Low - There is limited or no impact to the government operations
Sustainability / Resiliency | High - The initiative helps promote the cause of sustainability / resiliency for government services and operations (including infrastructure, security, training and capacity development) Medium - The initiative indirectly promotes or will direct the role for further improving the sustainability and resiliency of government Low - There is limited or no linkage to sustainability / resiliency
Execution complexity
People | High - impacts a broad user group (25,000++) or requires a high level of digital training and capacity development Medium - impacts moderate user base (5,000-25,000) or requires basic digital training and capacity development Low - impacts low user based (0 - 5,000) and does not require digital training and capacity development
Process | High - requires a high level of process re-engineering because of digital Medium - has process optimization or fine-tuning and does not require change in process Low - there is no change in process or service
Policy | High - initiaitve is dependent on the development of a new policy with considerable impact across the nation Medium - initiaitve requires changes to an existing policy and has limited impact Low - there is no impact to policy (new or existing)
Technology | High - initiative involves technology (skills / capability / solutions) which are new and requires high customization or development efforts. There is a significant potential for user resistance. Medium - moderate complexity where technology is reusable and has been tested/implemented in other instances (countries) Low - low complexity considering the solutions / skill set is available locally and high confidence exists in acceptance and implementation capability
Risks | High - high risk owing to extended timelines, project complexity, digital skills augmentation or resistance which may result in failure Medium - moderate risk owing to digital skills augmentation or resistance Low - low risk considering the initiative is a quick-win or limited / no digital skills augmentation
Timelines | High - 18 months + Medium - 6 months to 18 months Low - 0 - 6 months
Cost range | High - USD 1M + Medium - USD 250,000 - 1M Low - USD 0 - 250,000

## Ideate
No | Initiative | Group | Organization | Dependency | Remarks
IN001 | ABC | 1- MDA / Entity specific service | XYZ
IN002 | ABC | 2 - Common / Shared / Reusable service
IN003 | ABC | 3 - Enhancement initiative
IN004 | ABC
IN005 | ABC
IN006 | ABC
IN007 | ABC
IN008 | ABC
IN009 | ABC
IN010 | ABC
IN011 | ABC
IN012 | ABC
IN013 | ABC
IN014 | ABC
IN015 | ABC
IN016 | ABC
IN017 | ABC
IN018 | ABC
IN019 | ABC
IN020 | ABC
IN021 | ABC
IN022 | ABC
IN023 | ABC
IN024 | ABC
IN025 | ABC
IN026 | ABC
IN027 | ABC
IN028 | ABC
IN029 | ABC
IN030 | ABC
IN031 | ABC
IN032 | ABC
IN033 | ABC
IN034 | ABC
IN035 | ABC
IN036 | ABC
IN037 | ABC

## Align
No | Initiative | Build our people | Simplify lives | Boost sustainability and resiliency
IN001 | ABC | 1 | 0 | 1
IN002 | ABC
IN003 | ABC
IN004 | ABC
IN005 | ABC
IN006 | ABC
IN007 | ABC
IN008 | ABC
IN009 | ABC
IN010 | ABC
IN011 | ABC
IN012 | ABC
IN013 | ABC
IN014 | ABC
IN015 | ABC
IN016 | ABC
IN017 | ABC
IN018 | ABC
IN019 | ABC
IN020 | ABC
IN021 | ABC
IN022 | ABC
IN023 | ABC
IN024 | ABC
IN025 | ABC
IN026 | ABC
IN027 | ABC
IN028 | ABC
IN029 | ABC
IN030 | ABC
IN031 | ABC
IN032 | ABC
IN033 | ABC
IN034 | ABC
IN035 | ABC
IN036 | ABC
IN037 | ABC

## Classify
No | Initiative | Organization | Quick-win | Procurement | Standardization or compliance | Policy | Localisation | Status | Service offering /Background functions | Reusability / Shared service | Quick win description
IN001 | ABC | XYZ | 1 | 1 | 1 | 1 | 1 | Ongoing
IN002 | ABC | 0 | [5 empty] | Planned
IN003 | ABC | 0 | [5 empty] | Proposed
IN004 | ABC | 0
IN005 | ABC | 0
IN006 | ABC | 0
IN007 | ABC | 0
IN008 | ABC | 0
IN009 | ABC | 0
IN010 | ABC | 0
IN011 | ABC | 0
IN012 | ABC | 0
IN013 | ABC | 0
IN014 | ABC | 0
IN015 | ABC | 0
IN016 | ABC | 0
IN017 | ABC | 0
IN018 | ABC | 0
IN019 | ABC | 0
IN020 | ABC | 0
IN021 | ABC | 0
IN022 | ABC | 0
IN023 | ABC | 0
IN024 | ABC | 0
IN025 | ABC | 0
IN026 | ABC | 0
IN027 | ABC | 0
IN028 | ABC | 0
IN029 | ABC | 0
IN030 | ABC | 0
IN031 | ABC | 0
IN032 | ABC | 0
IN033 | ABC | 0
IN034 | ABC | 0
IN035 | ABC | 0
IN036 | ABC | 0
IN037 | ABC | 0

## Candidate initiatives
No | Initiative | Organization | Phase | Theme
IN001 | ABC | XYZ | Quick-win (0-6 months) | Build our people
IN002 | ABC | 0 | Phase 1 (6 -12 months) | Simplify lives
IN003 | ABC | 0 | Phase 2 (1 - 2 years) | Boost resilience and sustainability
IN004 | ABC | 0
IN005 | ABC | 0
IN006 | ABC | 0
IN007 | ABC | 0 |  |  | Phase | Theme
IN008 | ABC | 0 |  |  | Quick-win (0-6 months) | Build our people
IN009 | ABC | 0 |  |  | Phase 1 (6 -12 months) | Simplify lives
IN010 | ABC | 0 |  |  | Phase 2 (1 - 2 years) | Boost resilience and sustainability
IN011 | ABC | 0
IN012 | ABC | 0
IN013 | ABC | 0
IN014 | ABC | 0
IN015 | ABC | 0
IN016 | ABC | 0
IN017 | ABC | 0
IN018 | ABC | 0
IN019 | ABC | 0
IN020 | ABC | 0
IN021 | ABC | 0
IN022 | ABC | 0
IN023 | ABC | 0
IN024 | ABC | 0
IN025 | ABC | 0
IN026 | ABC | 0
IN027 | ABC | 0
IN028 | ABC | 0
IN029 | ABC | 0
IN030 | ABC | 0
IN031 | ABC | 0
IN032 | ABC | 0
IN033 | ABC | 0
IN034 | ABC | 0
IN035 | ABC | 0
IN036 | ABC | 0
IN037 | ABC | 0

## Initiative Budget Summary
No | Initiative | Organization | DTA | Phase | Theme | Localisation | Start Year | Support duration (Years) | Implementation time (months) | Services / schemes | Internal resources | Resource compensation budget | Procurement budget | Implementation cost | Annual support | Support cost | Total Budget | Budget 2025 | Budget 2026 | Budget 2027 | Total (2025-27)
IN001 | ABC | XYZ | Yes | Quick-win (0-6 months) | Build our people | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN002 | ABC | 0 | No | Phase 1 (6 -12 months) | Simplify lives | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN003 | ABC | 0 |  | Phase 2 (1 - 2 years) | Boost resilience and sustainability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN004 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN005 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN006 | ABC | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN007 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN008 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN009 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN010 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN011 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN012 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN013 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN014 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN015 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN016 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN017 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN018 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN019 | ABC | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN020 | ABC | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN021 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN022 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN023 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN024 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN025 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN026 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN027 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN028 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN029 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN030 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN031 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN032 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN033 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN034 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN035 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN036 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IN037 | ABC | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! |  | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | TOTAL (in USD M) | [12 empty] | #REF! | #REF! | #REF! | #REF!

## Initiaitive Budget detailed
No | Initiative | Organization | Localisation | Estimated Start Year | Estimated Support duration (Years) | Estimated Implementation time (months) | Indicative count of services / schemes / others to be associated | Internal resources required | Estimated Resource compensation budget | Procurement budget | Implementation cost | Annual support | Total Support cost | Total Budget (3 years) | Budget 2025 | Budget 2026 | Budget 2027
IN001 | ABC | XYZ | 1
IN002 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN003 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN004 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN005 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN006 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN007 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN008 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN009 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN010 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN011 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN012 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN013 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN014 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN015 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN016 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN017 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN018 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN019 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN020 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN021 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN022 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN023 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN024 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN025 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN026 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN027 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN028 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN029 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN030 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN031 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN032 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN033 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN034 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN035 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN036 | ABC | 0 | [12 empty] | 0 | 0 | 0
IN037 | ABC | 0 | [12 empty] | 0 | 0 | 0
TOTAL (in USD M) | [13 empty] | 0 | 0 | 0 | 0

## Prioritize
No | Initiative | Organization | Governance | Service delivery | Ease of operations | Sustainability / Resiliency | People | Process | Policy | Technology | Timelines | Risk | Resources compensation | Procurement Cost | Score | Benefit score | Execution score | Cost score | Risk score | Time score | Governance - Score | Service score | Ops Score | Sustainability score | People score | Process score | Policy score | Tech score | Cost
IN001 | ABC | XYZ
IN002 | ABC | 0
IN003 | ABC | 0
IN004 | ABC | 0
IN005 | ABC | 0
IN006 | ABC | 0
IN007 | ABC | 0
IN008 | ABC | 0
IN009 | ABC | 0
IN010 | ABC | 0
IN011 | ABC | 0
IN012 | ABC | 0
IN013 | ABC | 0
IN014 | ABC | 0
IN015 | ABC | 0
IN016 | ABC | 0
IN017 | ABC | 0
IN018 | ABC | 0
IN019 | ABC | 0
IN020 | ABC | 0
IN021 | ABC | 0
IN022 | ABC | 0
IN023 | ABC | 0
IN024 | ABC | 0
IN025 | ABC | 0
IN026 | ABC | 0
IN027 | ABC | 0
IN028 | ABC | 0
IN029 | ABC | 0
IN030 | ABC | 0
IN031 | ABC | 0
IN032 | ABC | 0

## Prioritization matrix
List of Initiatives |  | Overall Priority |  | Quotient Score (1 to 10) |  |  |  |  | Business benefits |  |  |  | Quantitative scoring of each business lever |  |  |  | Benefit Quotient |  |  |  | Execution Complexity |  |  |  | Execution Complexity |  |  |  | Execution Complexity Quotient |  |  | Cost |  |  |  | Risks |  | Timelines
No | Initiative Name | Score | Rating | Benefit quotient | Execution quotient | Cost quotient | Risk quotient | Time quotient | Governance | Service delivery | Ease of operations | Sustainability / Resiliency | Governance | Ease of business | Accessibility | Monitoring Management and Reporting | Absolute Score | Relative Score | Relative score scaled to 10 |  | People | Process | Policy | Technology | People | Process | Policy | Technology | Absolute Score | Relative score | Relative score scaled to 10 | Cost | Score (from 1 to 10) |  |  | Risk | Score (from 1 to 10) | Start time | Duration | Score (from 1 to 10)
|  |  |  | 25% | 25% | 25% | 25% | 25%
IN001 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN002 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN003 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2018-19 | 0 | #N/A
IN004 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2018-19 | 0 | #N/A
IN005 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2018-19 | 0 | #N/A
IN006 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2018-19 | 0 | #N/A
IN007 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN008 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN009 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2018-19 | 0 | #N/A
IN010 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN011 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2018-19 | 0 | #N/A
IN012 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2018-19 | 0 | #N/A
IN013 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN014 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN015 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN016 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN017 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN018 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN019 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN020 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN021 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2018-19 | 0 | #N/A
IN022 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN023 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN024 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN025 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN026 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN027 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2020-21 | 0 | #N/A
IN028 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2018-19 | 0 | #N/A
IN029 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2018-19 | 0 | #N/A
IN030 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2018-19 | 0 | #N/A
IN031 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
IN032 | ABC | #N/A | #N/A | 0 | 0 | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0 | 0 | #N/A |  |  | 0 | #N/A | 2016-17 | 0 | #N/A
[20 empty] | High | 0 | 0 | 0 | 0 | [10 empty] | High | 0
|  | #N/A | Low | [16 empty] | Medium | 0 | 0 | 0 | 0 | [10 empty] | Medium | 0
|  | #N/A | High | [16 empty] | Low | 0 | 0 | 0 | 0 | [10 empty] | Low | 0
|  | #N/A | Median
|  | #N/A | Average | [5 empty] | Weights
|  | #N/A | Quartile 1 | [5 empty] | 1 | 1 | 1 | 1
|  | #N/A | Quartile 2 | [5 empty] | Beneficial Impact level | Assigned Score - Option 1 | [10 empty] | Ease of Implementation level | Assigned Score | [9 empty] | Cost from | Cost to | Score |  | Risk & Complexity | Score |  | Implementation duration | Score
|  | #N/A | Quartile 3 | [5 empty] | High | 5 | [10 empty] | High | 1 | [9 empty] | 0 | 0.25 | 10 |  | Low | 7.5 |  | Low | 10
[9 empty] | Low | 1 | [10 empty] | Medium | 3 | [9 empty] | 0.25 | 0.5 | 8 |  | Medium | 5 |  | Medium | 7
|  | high count | 0 | [5 empty] | Medium | 3 | [10 empty] | Low | 5 | [9 empty] | 0.5 | 0.75 | 6 |  | High | 2.5 |  | High | 5
|  | medium count | 0 | [5 empty] | NA | 0 | [21 empty] | 0.75 | 1 | 4 | [5 empty] | 0
|  | low count | 0 | [17 empty] | Max possible score | 5 | [9 empty] | 1 | 2 | 2
[9 empty] | Max possible score | 5 | 0 | [9 empty] | # parameters | 4 | [9 empty] | 2 | 50 | 1 |  |  |  | 2016-17 | 20
[9 empty] | # business levers | 4 | 4 | [9 empty] | Total max possible score | 20 | [15 empty] | 2018-19 | 11
[9 empty] | Total max possible score | 20 | 0 | [26 empty] | 2020-21 | 1